## Costing
| TOTAL w/o U.P. | 1823.75 | hrs
| TOTAL w/o U.P. | 107.6012 | k€
| F | 10 | k€
| TOAL with F | 117.6012 | k€
Phase | Item | Effort (Hrs)
Co-engineering | Report and track all bugs features needed to commercialize the product | 80
Specification | Identified the scope of the first release | 16
Specification | Identification of our beta testers | 8
Design | Stats layout and bilans layout | 16
Coding & Verification | Fix minor issue from prototype | 40
Coding & Verification | Develop user roles | 40
Coding & Verification | Change firebase ui by full primitive firebase ui | 40
Coding & Verification | Create the footer ( displaying copyriht, contact, law) | 40
Coding & Verification | Implement a subscription system | 80
Coding & Verification | Implement Stats layout and bilans layout | 80
Coding & Verification | Prototype python IA serveur | 300
Coding & Verification | Configure the deployment server | 60
Coding & Verification | Transform home-page to a commercial product | 100
Coding & Verification | Wrapper Docotlib | 200
Coding & Verification | Install the development environment on dev server ( JIRA, gitlab, nexus ?, jenkins ? ) | 80
Validation | Validation with operationnal usage with our beta users | 80
Delivery |  | 40
Support to installation and Training | 5% of the Coding&Verification phase (CIDL, user manual, installation doc, exploitation doc, release note) | 53
Bug fixes & tuning during end-user validation | 10% of the Coding&Verification phase | 106
Maintenance & Support (post Entry Into Service) | Provision for minor evolution & support after deployment | 0
Project Management | 15% of Project Management | 218.85
Provision for risk | 10% of estimation uncertainty | 145.9
F | Buy 4 laptops and 2 servers + associated furnitures | 10

## Config
UO RATE | 118%
Hourly cost | 50